## Version Roadmap
DATA247 — Version Roadmap ¦ V1.0 Launch vs V2.0 Growth
Realistic roadmap based on user feedback and revenue — no over-commitment
# | Feature | Version 1.0 (Launch) | Version 2.0 (Post-Launch) | Reason for Phasing
CONTENT & PRACTICE
1 | MCQ Practice | 6 modules x 3 levels — DA and DS | Business Analyst, ML Engineer tracks added | Content creation needed post-launch
2 | Flashcards | DA and DS tracks — flip card system | BA and ML Engineer flashcards | Content post-launch
3 | Morning Drill | 5 daily questions — date-based | Auto-scheduling — no manual upload needed | Technical complexity — Month 2
4 | Job Ready Quiz | DA and DS — 10 questions each | BA and ML Engineer quizzes | Content post-launch
5 | Company Packs | Coming Soon — user can register interest | TCS, Infosys, Wipro, GIFT City packs | Content creation needed
TOOLS
6 | Salary Calculator | Education, city, role, skills — salary range | City-specific data updated quarterly | Manual update initially
7 | Job Alerts | Weekly manual update by founder | Automated feed integration | Month 2
GROWTH
8 | Referral System | Referral code — reward on signup | Tiered referral rewards | Month 2
9 | WhatsApp Community | Direct join link in app | Verified entry — app account required | Needs user base first
10 | Campus Outreach | Coming Soon | Campus Ambassador programme | Month 3+
MONETISATION
11 | Pro Subscription | Coming Soon — user can register interest | Rs 99/month via payment gateway | After 500 users established
12 | Company Packs (Paid) | — | Premium packs for specific companies | Month 3
ENGAGEMENT
13 | Streak System | Daily drill streak — milestone messages | Streak freeze feature | Month 2
14 | Bookmarks | Save questions and flashcards | Smart revision reminders | Month 3
15 | What's Coming | 7 features — Notify Me button | Becomes real features progressively | Ongoing
PLATFORM
16 | Web App (PWA) | Live — mobile-first — works on all devices | — | Complete
17 | Play Store | Submission planned post-beta | Full Play Store presence | After beta testing
18 | Admin Panel | News, Drills, Jobs, Questions, Flashcards, Users | Analytics dashboard improvements | Month 2
COMPETITION & SOCIAL
19 | 1v1 Battle Arena | Coming Soon | Real-time MCQ duels | Needs large active user base — Month 4+
20 | National Leaderboard | Coming Soon | Top 100 users — weekly rankings | Needs 5000+ users
21 | AI Mock Interview | Coming Soon | AI-powered 5-minute practice interview | Complex — Month 4+
22 | Skill Spider Map | Coming Soon | Visual radar chart of skill strengths | Month 3+
🟢 Green = Built in V1.0 🟠 Orange = Coming Soon in V1.0 ⬜ White = V2.0 Feature