## Development Phases
DATA247 — Development Record v1.0
Pre-development planning document ¦ May 2026 ¦ Vijetasingh Rajput
Phase 1 — Project Initiation ¦ Target: April 2026
Task ID | Task | Description | Target Date | Status
1.1 | Concept ideation and market research | Identify gap in India data job preparation market | April 2026 | Completed
1.2 | GitHub repository creation | Set up public documentation repository | April 2026 | Completed
1.3 | Product vision and scope definition | Define target audience, roles, and product direction | April 2026 | Completed
1.4 | Competitor analysis | Review InterviewBit, GeeksforGeeks, Adda247 and similar platforms | April 2026 | Completed
1.5 | Initial feature architecture planning | Define high level feature list for V1.0 | April 2026 | Completed
Phase 2 — Planning and Compliance ¦ Target: May 2026
Task ID | Task | Description | Target Date | Status
2.1 | Pre-build product scrutiny | Identify and resolve 20 potential issues before development | May 2026 | Completed
2.2 | Master planning document | Create comprehensive planning and compliance document | May 2026 | Completed
2.3 | DPDP Act 2023 compliance review | Review requirements and define compliance actions | May 2026 | Completed
2.4 | Brand standards definition | Define colors, typography, language strategy and identity | May 2026 | Completed
2.5 | Infrastructure planning | Define database, hosting, authentication and admin panel architecture | May 2026 | Completed
2.6 | Content strategy | Define question bank structure, flashcard format and interview guide format | May 2026 | Completed
2.7 | Salary calculator formula | Define complete salary calculation formula based on India 2026 market data | May 2026 | Completed
Phase 3 — Core Development ¦ Target: May 2026
Task ID | Task | Description | Target Date | Status
3.1 | Authentication system | Email and Google login, role selection, consent checkbox, age verification | May 2026 | Completed
3.2 | Home screen | Personalised greeting, stats bar, news section, Telegram button, feature cards | May 2026 | Completed
3.3 | MCQ practice module | Question bank with role, topic and difficulty filters. Timer and results screen. | May 2026 | Completed
3.4 | Flashcards module | 3D flip animation, sliding drawer filter, bookmark functionality | May 2026 | Completed
3.5 | Morning drill module | 5 daily questions, countdown timer, streak system, shareable score card | May 2026 | Completed
3.6 | Job ready quiz | 10 questions per role, scoring system, skill gap analysis | May 2026 | Completed
3.7 | Salary calculator | Multi-input calculator with India 2026 salary formula and range output | May 2026 | Completed
3.8 | Interview guides | HR, Technical, Behavioural and Managerial rounds with flip card reader | May 2026 | Completed
3.9 | Learning roadmap | 12-week personalised plan by role and experience level | May 2026 | Completed
3.10 | Bookmarks system | Save and organise questions and flashcards | May 2026 | Completed
3.11 | Referral system | Unique code generation, referral tracking, reward system | May 2026 | Completed
Phase 4 — Admin Panel ¦ Target: May 2026
Task ID | Task | Description | Target Date | Status
4.1 | Admin authentication | Restricted login for data247official@gmail.com only | May 2026 | Completed
4.2 | News management | RSS feed integration, manual news add, featured toggle, auto delete | May 2026 | Completed
4.3 | Question management | CSV bulk import, role/level/topic filter, load and delete | May 2026 | Completed
4.4 | Flashcard management | CSV bulk import, filtering, select and delete | May 2026 | Completed
4.5 | Interview guides management | CSV upload, role and category filter | May 2026 | Completed
4.6 | Morning drill management | CSV upload, date range management, auto delete after 1 day | May 2026 | Completed
4.7 | User management | View all users, block and unblock, delete accounts | May 2026 | Completed
4.8 | Notifications management | Waitlist counts for V2.0 features, export emails | May 2026 | Completed
4.9 | Feedback management | View user feedback, mark read, export to CSV | May 2026 | Completed
Phase 5 — Launch Preparation ¦ Target: May to June 2026
Task ID | Task | Description | Target Date | Status
5.1 | Content upload | Upload all MCQ questions, flashcards, interview guides and morning drills | May 2026 | Completed
5.2 | Security audit | Apply Row Level Security on all database tables, check for vulnerabilities | May to June 2026 | Completed
5.3 | Demo account creation | Create demo account for Play Store reviewers | June 2026 | Completed
5.4 | Legal pages | Privacy Policy and Terms of Service pages with DPDP Act 2023 compliance | May 2026 | Completed
5.5 | Testing on mobile devices | Full checklist testing on phone before submission | June 2026 | Completed
5.6 | App publication | Publish app at the official DATA247 app URL for public access | June 2026 | Completed
5.7 | Play Store submission | Submit app to Google Play Store | June 2026 | In Progress
5.8 | Community launch | Launch Telegram community and LinkedIn company page | May to June 2026 | Completed