## Product Plan
DATA247 — Product Overview ¦ Founder: Vijetasingh Rajput ¦ 2026
EdTech interview preparation app for Data Analysts and Data Scientists in India — Bootstrapped startup
App Identity & Market Position
App Name |  | DATA247
Tagline |  | From College to Cabin
Category |  | EdTech — Data Career Interview Preparation
Target Roles |  | Data Analyst, Data Scientist
Target Users |  | College students and freshers in India preparing for data jobs
Primary Market |  | India — Tier 1, Tier 2, and Tier 3 cities
Secondary Market |  | Indian diaspora — UK, USA, Canada, Australia
Language |  | Simple English — accessible to all Indian users regardless of region
Founder |  | Vijetasingh Rajput — sole founder
Business Model |  | Bootstrapped — self-funded — no external investment
Founder Role |  | Product strategy, content creation, market research, legal compliance, business direction
Development |  | Built using modern no-code development platforms — founder led product
Contact |  | data247official@gmail.com
Market Opportunity — India Data Jobs
Sector growth |  | Data and Analytics roles are among the fastest growing in India — significant demand across Tier 1, 2, and 3 cities
Education gap |  | No structured, accessible, beginner-to-advanced interview preparation app exists specifically for data roles in India
Language gap |  | Existing platforms use complex or advanced English — not accessible to students in smaller cities
Pricing gap |  | Existing platforms price at Rs 299-999 per month — DATA247 targets Rs 99 per month — most accessible option
Content gap |  | No single platform covers SQL, Python, Excel, Power BI, Statistics, ML, and AI preparation together with levelled content
Unique differentiator |  | DATA247 combines: structured levelled content + daily practice habit + salary calculator + job alerts — no competitor offers all four
Version 1.0 — Confirmed Features
# | Feature | Description | User Benefit | Track | Status
1 | MCQ Practice | Topic and level-based multiple choice questions with instant feedback | Structured preparation — know exactly where you stand | DA + DS | Live
2 | 3-Level System | Beginner, Intermediate, Advanced per topic — user progresses at own pace | No overwhelm — start where you are | DA + DS | Live
3 | Flashcards | Flip card system for concept and formula revision | Quick recall — revision made simple | DA + DS | Live
4 | Morning Drill | 5 mixed questions daily — builds consistent practice habit | Daily habit formation — like Duolingo for data jobs | DA + DS | Live
5 | Streak System | Tracks consecutive days of practice — milestone rewards | Motivation to return daily | DA + DS | Live
6 | Job Ready Quiz | 10-question diagnostic — gives percentage job readiness score | Honest assessment — know if ready to apply | DA + DS | Live
7 | Salary Calculator | Estimates data job salary based on education, city, role, skills | Viral sharing feature — personalised career insight | DA + DS | Live
8 | Job Alerts | Weekly curated data job listings — updated every Sunday | Saves time — relevant jobs in one place | DA + DS | Live
9 | Bookmarks | Save questions and flashcards for revision | Personalised revision list | DA + DS | Live
10 | Referral System | Unique code per user — both inviter and new user receive reward on signup | Word-of-mouth growth engine | All | Live
11 | What's Coming | Preview of upcoming features — users register interest | Anticipation and retention | All | Live
12 | Admin Panel | Founder-only content management — news, drills, jobs, questions, users | Full founder control — no third party dependency | Admin | Live
13 | Privacy Policy | DPDP Act 2023 compliant — inside app | Legal compliance — user trust | All | Live
14 | Terms of Service | Linked from signup and settings | Legal compliance | All | Live
15 | WhatsApp Community | Direct link to learner community inside app | Peer learning and engagement | All | Live
Data Analyst Track — 6 Modules x 3 Levels
Module | Topics Covered | Beginner | Intermediate | Advanced | Status
SQL | SELECT, WHERE, GROUP BY, JOIN, Subqueries, Aggregations, Window Functions, NULL handling | 20 Q | 20 Q | 20 Q | Live
Excel | VLOOKUP, HLOOKUP, INDEX MATCH, Pivot Tables, IF formulas, COUNTIF, SUMIF, Data Validation, Charts | 20 Q | 20 Q | 20 Q | Live
Python | Pandas, data cleaning, Matplotlib, NumPy basics, data analysis workflows | 20 Q | 20 Q | 20 Q | Live
Power BI | DAX basics, Measures vs Calculated columns, Relationships, Filters, Slicers, Visualisations | 20 Q | 20 Q | 20 Q | Live
Statistics | Mean, Median, Mode, Standard Deviation, Correlation, Normal Distribution, Hypothesis basics | 20 Q | 20 Q | 20 Q | Live
AI for Analysts | AI tools for data work, ChatGPT for analysis, Copilot, basic prompting, AI-assisted workflows | 20 Q | 20 Q | 20 Q | Live
TOTAL — Data Analyst |  | 120 Q | 120 Q | 120 Q | 360 questions
Data Scientist Track — 6 Modules x 3 Levels
Module | Topics Covered | Beginner | Intermediate | Advanced | Status
SQL | Advanced JOINs, Window Functions (ROW_NUMBER, RANK, LAG, LEAD), CTEs, Query optimisation, Indexing | 20 Q | 20 Q | 20 Q | Live
Python | Scikit-learn, ML pipelines, advanced Pandas, model evaluation metrics, Feature engineering | 20 Q | 20 Q | 20 Q | Live
Statistics | Probability, Distributions (Normal, Binomial, Poisson), A/B Testing, Confidence Intervals, Regression | 20 Q | 20 Q | 20 Q | Live
Machine Learning | Supervised vs Unsupervised, Regression, Decision Trees, Random Forest, KNN, SVM, Cross Validation, Evaluation metrics | 20 Q | 20 Q | 20 Q | Live
Deep Learning | Neural networks, CNNs, model deployment basics, transfer learning concepts | 20 Q | 20 Q | 20 Q | Live
AI and GenAI | LLMs, Transformers, RAG, Prompt Engineering, Fine-tuning, AI Ethics, Model deployment | 20 Q | 20 Q | 20 Q | Live
TOTAL — Data Scientist |  | 120 Q | 120 Q | 120 Q | 360 questions
Total Content Ready for Launch
Content Type | Breakdown | Quantity | Status
MCQ Questions — Data Analyst | 6 modules x 3 levels x 20 questions | 360 questions | Ready
MCQ Questions — Data Scientist | 6 modules x 3 levels x 20 questions | 360 questions | Ready
Flashcards — Data Analyst | 6 modules — concept and formula cards | 120+ cards | Ready
Flashcards — Data Scientist | 6 modules — concept and formula cards | 120+ cards | Ready
Morning Drill Sets | 30 daily sets — 5 mixed questions each | 150 questions | Ready
Job Ready Quiz | Data Analyst + Data Scientist — 10 questions each | 20 questions | Ready
GRAND TOTAL | All content uploaded to database | 900+ pieces | Complete

## Version Roadmap
DATA247 — Product Roadmap ¦ Version 1.0 → Version 2.0
Phased delivery — Version 1.0 launches core product — Version 2.0 adds growth features post user validation
# | Feature Area | Version 1.0 — At Launch | Version 2.0 — Post Launch | Rationale
CONTENT
1 | MCQ Practice | Data Analyst and Data Scientist — 6 modules each — 3 levels — 360 questions per track | Business Analyst, ML Engineer, Data Engineer tracks added based on user demand | Launch with two highest-demand tracks — expand based on data
2 | Flashcards | Data Analyst and Data Scientist — all modules — flip card system | Additional tracks as content is created post-launch | Same as MCQ — demand-led expansion
3 | Morning Drill | 30 days of daily drills pre-loaded — manually updated by founder weekly | Automated scheduling — no manual upload required | Manual is sufficient for launch — automation added when user base justifies
4 | Job Ready Quiz | Data Analyst and Data Scientist — 10 questions each — MCQ format | Additional role quizzes added based on user feedback | Core two roles at launch
5 | Company Packs | Shown as Coming Soon — users can register interest | TCS, Infosys, Wipro, Accenture, GIFT City Fintech packs — Pro feature | Content creation needed — post-launch priority based on Notify Me data
USER TOOLS
6 | Salary Calculator | Education, city, role, experience, skills — salary range output — WhatsApp share | Quarterly data update — more granular city data | Core feature at launch — data refined post-launch
7 | Job Alerts | Weekly curated listings — manually updated every Sunday by founder | Automated job feed integration | Manual is manageable at launch — automation at scale
8 | Bookmarks | Save questions and flashcards — organised by type | Smart revision reminders based on saved content | Core feature at launch — smart features added later
GROWTH
9 | Referral System | Unique code per user — reward on successful signup — both users benefit | Tiered referral rewards — leaderboard for top inviters | Core referral live at launch — gamification added at scale
10 | WhatsApp Community | Direct join link inside app — founder manages manually | Verified entry system — app account required to join | Open community at launch — verification when community exceeds 500
11 | Campus Outreach | Coming Soon — shown on What's Coming screen | Formal campus ambassador programme | Requires user base — planned for Month 3 onwards
MONETISATION
12 | Pro Subscription | Shown as Coming Soon — users can register interest | Rs 99 per month via payment gateway — unlocks premium features | Launched after first 500 users — trust established before monetisation
13 | Premium Company Packs | Not available | Paid packs for specific company interview preparation | Month 3 onwards — after Pro subscription established
ENGAGEMENT
14 | Streak System | Daily drill streak — 7, 30, 100 day milestone celebrations | Streak freeze feature — once per month protection | Core streak live — freeze added as user requests it
15 | What's Coming Screen | 7 upcoming features — Notify Me button — user interest registered | Features progressively become real as development completes | Ongoing — creates anticipation and reduces churn
PLATFORM
16 | Web App | Mobile-first progressive web app — works on all devices and browsers | Native app experience improvements | PWA sufficient for launch
17 | Play Store | Submission planned after beta validation | Full Play Store presence — ratings and reviews | Post-beta — after product stability confirmed
18 | Admin Panel | Full content management — news, drills, jobs, questions, flashcards, users | Analytics improvements — user behaviour insights | Complete at launch — improvements ongoing
FUTURE FEATURES
19 | 1v1 Battle Arena | Coming Soon | Real-time MCQ duels between users | Requires active user base of 2000+ — Month 4 onwards
20 | National Leaderboard | Coming Soon | Top 100 users nationally — weekly and monthly rankings | Requires 5000+ active users to be meaningful
21 | AI Mock Interview | Coming Soon | Short AI-powered practice interview with feedback | Complex feature — planned for Month 4 onwards
22 | Skill Spider Map | Coming Soon | Visual radar chart showing strength across all skill areas | Data visualisation feature — Month 3 onwards
Green = Live in Version 1.0 Orange = Coming Soon placeholder in V1.0 White = Version 2.0 feature

## Development Record
DATA247 — Development Record ¦ Phase-by-Phase Progress
Complete record of product development — from concept to live app — founder led throughout
# | Phase | Area | What Was Completed | Output / Evidence | Status
PHASE 1 — CONCEPT & RESEARCH
1 | Research | Market Analysis | Identified gap in India's data job interview preparation market — no structured, accessible, levelled app existed for DA and DS roles | Market gap documented | Complete
2 | Research | Competitor Analysis | Reviewed existing platforms — InterviewBit, GeeksforGeeks, Adda247 — identified pricing, language, and content gaps | Competitor landscape mapped | Complete
3 | Research | User Research | Identified target user — college students and freshers in Tier 2/3 cities — understood their preparation challenges | User persona defined | Complete
4 | Concept | Product Vision | Defined core product vision — From College to Cabin — structured levelled preparation for data careers | Vision and tagline established | Complete
5 | Concept | Feature Planning | Defined full feature set — Version 1.0 and Version 2.0 — documented in planning files | Feature plan documented | Complete
6 | Concept | Legal Compliance | Reviewed India DPDP Act 2023 — implemented all required compliance measures — Privacy Policy, Terms of Service, age verification, data deletion | DPDP Act compliance complete | Complete
7 | Concept | Brand Identity | Established brand standards — name DATA247, tagline, color system, language standard — Simple English throughout | Brand guidelines defined | Complete
8 | Documentation | GitHub | Created GitHub repository — all planning documentation committed — original timestamps preserved | GitHub repo with timestamps | Complete
9 | Documentation | Master Document | Comprehensive pre-build planning document created — product overview, legal compliance, scrutiny results, brand standards | Master Document v2.0 | Complete
10 | Documentation | Idea Timestamp | Formal idea documentation sent via email to self — timestamped evidence of original concept | Email timestamp secured | Complete
PHASE 2 — CONTENT CREATION
11 | Content | SQL — Data Analyst | Written 60 questions across Beginner, Intermediate, and Advanced levels — simple English — clear explanations | 60 questions ready | Complete
12 | Content | Excel — Data Analyst | Written 60 questions — VLOOKUP, Pivot Tables, formulas — all three levels | 60 questions ready | Complete
13 | Content | Python — Data Analyst | Written 60 questions — Pandas, data cleaning, visualisation — all three levels | 60 questions ready | Complete
14 | Content | Power BI — Data Analyst | Written 60 questions — DAX, dashboards, relationships — all three levels | 60 questions ready | Complete
15 | Content | Statistics — Data Analyst | Written 60 questions — mean, median, correlation, hypothesis — all three levels | 60 questions ready | Complete
16 | Content | AI for Analysts — DA | Written 60 questions — AI tools, ChatGPT for analysis, prompting — all three levels | 60 questions ready | Complete
17 | Content | SQL — Data Scientist | Written 60 questions — advanced queries, window functions, optimisation — all three levels | 60 questions ready | Complete
18 | Content | Python — Data Scientist | Written 60 questions — Scikit-learn, ML pipelines, model evaluation — all three levels | 60 questions ready | Complete
19 | Content | Statistics — Data Scientist | Written 60 questions — probability, distributions, A/B testing — all three levels | 60 questions ready | Complete
20 | Content | Machine Learning | Written 60 questions — algorithms, evaluation metrics, feature engineering — all three levels | 60 questions ready | Complete
21 | Content | Deep Learning | Written 60 questions — neural networks, CNNs, deployment — all three levels | 60 questions ready | Complete
22 | Content | AI and GenAI — DS | Written 60 questions — LLMs, RAG, prompt engineering, fine-tuning — all three levels | 60 questions ready | Complete
23 | Content | Flashcards — DA | Created 120+ flashcards for all Data Analyst modules — concept and formula cards | 120+ cards ready | Complete
24 | Content | Flashcards — DS | Created 120+ flashcards for all Data Scientist modules | 120+ cards ready | Complete
25 | Content | Morning Drill | Written 30 days of daily drill sets — 5 questions each — mixed topics | 150 questions ready | Complete
26 | Content | Job Ready Quiz | Written 10 diagnostic questions each for Data Analyst and Data Scientist | 20 questions ready | Complete
PHASE 3 — PRODUCT DEVELOPMENT
27 | Development | Architecture | Defined complete app architecture — screens, navigation, database schema, user flows — before any development began | Architecture documented | Complete
28 | Development | Authentication | Built login and signup — email and Google — age verification, consent checkbox, role selection, referral code entry | Auth system live | Complete
29 | Development | Home Screen | Built personalised home screen — greeting, stats bar, news, WhatsApp community button, salary calculator teaser | Home screen live | Complete
30 | Development | MCQ Practice | Built complete MCQ system — topic and level selection, sliding drawer navigation, questions, instant feedback, explanations, bookmarks, results screen with review | MCQ system live | Complete
31 | Development | Flashcards | Built flashcard system — 3D flip animation, topic and role navigation, save to bookmarks | Flashcard system live | Complete
32 | Development | Morning Drill | Built daily drill — 5 questions, 5 minute countdown timer, streak tracking, shareable score card | Morning Drill live | Complete
33 | Development | Streak System | Built streak tracking — daily drill streak — milestone messages at 7, 30, 100 days | Streak system live | Complete
34 | Development | Job Ready Quiz | Built diagnostic quiz — role selection, 10 MCQ questions, score 0-100, skill gap analysis, review screen, WhatsApp share | Job Ready Quiz live | Complete
35 | Development | Salary Calculator | Built calculator — 5 inputs, formula-based salary range output, missing skills shown, WhatsApp share | Salary Calculator live | Complete
36 | Development | Job Alerts | Built job alerts section — weekly update system, role filter, Apply Now button | Job Alerts live | Complete
37 | Development | Referral System | Built referral system — unique code per user on signup, reward triggered on successful referral signup | Referral system live | Complete
38 | Development | Bookmarks | Built bookmark system — save questions and flashcards, organised by type, remove option | Bookmarks live | Complete
39 | Development | What's Coming | Built coming soon screen — 7 upcoming features, Notify Me button, interest registered in database | What's Coming live | Complete
40 | Development | Admin Panel | Built complete founder admin panel — 6 sections — News, Drills, Jobs, Questions, Flashcards, Users — CSV upload for bulk content management | Admin Panel live | Complete
41 | Development | Legal Pages | Built Privacy Policy and Terms of Service pages — DPDP Act 2023 compliant — accessible from signup | Legal pages live | Complete
42 | Development | Performance | Optimised app — caching, lazy loading, compatible with 2GB RAM devices — target under 30MB | Performance optimised | Complete
PHASE 4 — CONTENT UPLOAD & TESTING
43 | Upload | MCQ Questions | All 720 MCQ questions uploaded to database — correctly mapped to topic, role, and difficulty level | 720 questions live | Complete
44 | Upload | Flashcards | All flashcards uploaded — Data Analyst and Data Scientist tracks | 240+ cards live | Complete
45 | Upload | Morning Drills | 30 days of morning drill content uploaded — date-based delivery confirmed working | 30 drill sets live | Complete
46 | Testing | Functional Testing | All screens tested — login, signup, MCQ, flashcards, drill, quiz, calculator, job alerts, bookmarks, referral, admin | Testing complete | Complete
PHASE 5 — NEXT STEPS
47 | Next | Beta Launch | Share app with 20-50 users — collect structured feedback — prioritise fixes | Beta feedback collected | In Progress
48 | Next | Job Alerts | Add first batch of curated data job listings to admin panel | Job alerts populated | In Progress
49 | Next | News Section | Add first batch of data industry news to admin panel | News section live | In Progress
50 | Next | Bug Fixes | Resolve any issues identified during beta testing | Stable version | Planned
51 | Next | Play Store | Submit app to Google Play Store — after beta validation complete | App on Play Store | Planned
52 | Next | Pro Subscription | Launch Pro plan at Rs 99/month — after 500 users established | Revenue stream live | Planned

## Pricing & Revenue
DATA247 — Pricing Strategy & Revenue Model ¦ India EdTech Market
Conservative projections based on Indian EdTech benchmarks — trust first, monetisation second
Pricing Plans
Plan | Price | Billing Cycle | Included | Target User
Free | Rs 0 | Forever | MCQ practice, Morning Drill, Flashcards, Job Ready Quiz, Job Alerts, Salary Calculator, WhatsApp community link | All users — builds trust and habit
Pro Monthly | Rs 99 | Monthly | Everything in Free + Unlimited MCQ access, Full Flashcard library, Company Packs (V2.0), priority new features | Active job seekers — placement season
Pro Quarterly | Rs 249 | Every 3 months | Everything in Pro Monthly — saves Rs 48 versus monthly billing | Students in final year placement
Pro Yearly | Rs 799 | Annual | Everything in Pro Monthly — best value — saves Rs 389 versus monthly | Serious career changers — long-term learners
Pricing Rationale
Benchmark comparison |  | Adda247 Pro: Rs 299-999/month ¦ GeeksforGeeks: Rs 249/month ¦ DATA247 at Rs 99 is the most accessible option in the market
Target audience reality |  | Primary users are Tier 2/3 city students and freshers — Rs 99 is below the psychological Rs 100 barrier — decision is instant
Value proposition |  | One successful interview — one job offer — starting salary Rs 25,000-40,000/month — Rs 99 cost is less than 0.5% of first monthly salary
Monetisation timing |  | Pro plan launched after 500 free users — trust and habit established first — conversion rate higher when users already see value
Free plan strategy |  | Free plan is genuinely useful — not crippled — this builds word of mouth and referrals — organic growth before paid acquisition
Revenue Projections — Conservative Estimates Based on Indian EdTech Benchmarks
Milestone | Estimated Users | Pro at 5% Conversion | Monthly Revenue | Notes
Beta — Free only | 50 to 100 | No Pro yet | Rs 0 | Building product-market fit — no monetisation
Pro launch — Month 2 | 200 to 500 | 10 to 25 Pro users | Rs 990 to 2,475 | Pro launched after 500 users — conservative start
Month 3 | 500 to 1,000 | 25 to 50 Pro users | Rs 2,475 to 4,950 | Word of mouth growing — referral system active
Month 6 | 2,000 to 5,000 | 100 to 250 Pro users | Rs 9,900 to 24,750 | Company packs added — Play Store downloads contributing
Month 12 | 5,000 to 10,000 | 250 to 500 Pro users | Rs 24,750 to 49,500 | Stable recurring revenue — annual plan conversions
Year 2 | 20,000 to 50,000 | 1,000 to 2,500 Pro users | Rs 99,000 to 2,47,500 | Scale — BA and ML Engineer tracks added — campus partnerships
Note: All projections are estimates benchmarked against Indian EdTech industry data (Adda247, GeeksforGeeks conversion rates). Actual results will depend on user acquisition, product quality, market conditions, and execution. These are planning targets, not guarantees.
Key Business Metrics to Track Post-Launch
Metric | What It Measures | Target — Month 1 | Target — Month 3 | Target — Month 6
Daily Active Users | How many users open the app each day | 20+ | 200+ | 500+
Morning Drill Completion Rate | Percentage of users completing daily drill | 30%+ | 40%+ | 50%+
MCQ Questions per Session | Engagement depth per visit | 10+ | 15+ | 20+
Referral Rate | New users coming via referral codes | 10% | 20% | 30%
WhatsApp Community Members | Community size — engagement indicator | 50+ | 200+ | 500+
Pro Conversion Rate | Free to Pro upgrade percentage | N/A | 3-5% | 5-8%
Play Store Rating | User satisfaction indicator | N/A | 4.0+ | 4.2+