## Build Steps
DATA247 — Build Steps & Progress Tracker ¦ May 2026
Complete record of product development steps — tick Done column as each step is completed
# | Phase | Day / Week | Step — What Was Done | Output | Done
SETUP
1 | Setup | May 6 | Product concept conceived and documented | Idea document created | ✅
2 | Setup | May 6 | GitHub repository created — original timestamp | data247 repo live | ✅
3 | Setup | May 6 | Timestamp email sent to self — idea documentation | Email evidence secured | ✅
4 | Setup | May 6 | WhatsApp community created — two groups set up | Community ready | ✅
5 | Setup | May 6 | Development accounts created — database and hosting | Infrastructure ready | ✅
CONTENT CREATION
6 | Content | May 6-8 | SQL — Data Analyst — Beginner, Intermediate, Advanced questions written | 60 questions | ✅
7 | Content | May 6-8 | Excel — Data Analyst — Beginner, Intermediate, Advanced questions written | 60 questions | ✅
8 | Content | May 6-8 | Python — Data Analyst — Beginner, Intermediate, Advanced questions written | 60 questions | ✅
9 | Content | May 6-8 | Power BI — Data Analyst — Beginner, Intermediate, Advanced questions written | 60 questions | ✅
10 | Content | May 6-8 | Statistics — Data Analyst — Beginner, Intermediate, Advanced questions written | 60 questions | ✅
11 | Content | May 6-8 | AI for Analysts — Data Analyst — Beginner, Intermediate, Advanced questions written | 60 questions | ✅
12 | Content | May 6-8 | SQL — Data Scientist — Beginner, Intermediate, Advanced questions written | 60 questions | ✅
13 | Content | May 6-8 | Python — Data Scientist — Beginner, Intermediate, Advanced questions written | 60 questions | ✅
14 | Content | May 6-8 | Statistics — Data Scientist — Beginner, Intermediate, Advanced questions written | 60 questions | ✅
15 | Content | May 6-8 | Machine Learning — Data Scientist — all levels written | 60 questions | ✅
16 | Content | May 6-8 | Deep Learning — Data Scientist — all levels written | 60 questions | ✅
17 | Content | May 6-8 | AI and GenAI — Data Scientist — all levels written | 60 questions | ✅
18 | Content | May 6-8 | Flashcards written for all DA and DS modules | 240+ cards | ✅
19 | Content | May 6-8 | Morning Drill sets written — 30 days | 150 questions | ✅
20 | Content | May 6-8 | Job Ready Quiz written — DA and DS | 20 questions | ✅
PRODUCT PLANNING
21 | Planning | May 8 | Pre-build scrutiny conducted — 20 issues identified and resolved | Scrutiny document | ✅
22 | Planning | May 8 | Master planning and compliance document created | Master Document v2.0 | ✅
23 | Planning | May 8 | DPDP Act 2023 compliance reviewed and implemented | Legal compliance complete | ✅
24 | Planning | May 8 | Brand standards finalised — colors, tagline, language | Brand guidelines | ✅
25 | Planning | May 8 | Version roadmap created — V1.0 and V2.0 features defined | Version plan | ✅
APP DEVELOPMENT
26 | Build | May 8-10 | App architecture designed — screens, navigation, database tables | Architecture defined | ✅
27 | Build | May 8-10 | Login and signup built — age verification, consent, role selection | Auth complete | ✅
28 | Build | May 8-10 | Home screen built — greeting, stats, news, WhatsApp button | Home screen live | ✅
29 | Build | May 8-10 | MCQ Practice built — topic selection, questions, explanations, bookmarks | MCQ complete | ✅
30 | Build | May 8-10 | Flashcard system built — 3D flip animation, save feature | Flashcards live | ✅
31 | Build | May 8-10 | Morning Drill built — 5 questions, timer, streak system | Drill complete | ✅
32 | Build | May 8-10 | Job Ready Quiz built — MCQ format, score, review screen | Quiz live | ✅
33 | Build | May 8-10 | Salary Calculator built — formula-based range output | Calculator live | ✅
34 | Build | May 8-10 | Job Alerts built — weekly update system | Alerts live | ✅
35 | Build | May 8-10 | Referral system built — unique code per user, reward on signup | Referral live | ✅
36 | Build | May 8-10 | What's Coming screen built — Notify Me feature | Screen live | ✅
37 | Build | May 8-10 | Admin panel built — 6 sections, founder access only | Admin complete | ✅
38 | Build | May 8-10 | Privacy Policy and Terms of Service pages built — DPDP compliant | Legal pages live | ✅
39 | Build | May 8-10 | Performance optimised — caching, lazy loading, 2GB RAM compatible | Optimisation done | ✅
CONTENT UPLOAD
40 | Upload | May 10-11 | All MCQ questions uploaded to database — 720 questions | Questions live | ✅
41 | Upload | May 10-11 | All flashcards uploaded — DA and DS | Flashcards live | ✅
42 | Upload | May 10-11 | Morning Drill content uploaded — 30 days | Drills live | ✅
NEXT STEPS
43 | Next | Week 3 | Beta testing — share with 20-50 users, collect feedback | Beta feedback | ⏳
44 | Next | Week 3 | Job Alerts — first batch of jobs added | Job alerts live | ⏳
45 | Next | Week 3 | News section — first batch added | News live | ⏳
46 | Next | Week 4 | Bug fixes based on beta feedback | Stable version | ⏳
47 | Next | Month 2 | Play Store submission | App on Play Store | ⏳
48 | Next | Month 2 | Pro subscription launched | Revenue starts | ⏳