## V2.0 Development Phases
DATA247 — Development Record v2.0
V2.0 development planning document ¦ Post V1.0 launch ¦ Vijetasingh Rajput ¦ 2026
Phase 1 — V1.0 Stabilisation ¦ Target: Q3 2026 — July to September 2026
Task ID | Task | Description | Target Date | Feature Type | Status
1.1 | Bug fixes and improvements | Resolve all issues identified during V1.0 beta testing and user feedback | July to August 2026 | Free | To Do
1.2 | Play Store submission | Submit app to Google Play Store — complete ASO optimisation | July 2026 | Free | To Do
1.3 | User growth to 200 plus | Organic growth through referral system, Telegram community and LinkedIn | Q3 2026 | Free | To Do
1.4 | Notify Me data analysis | Analyse which V2.0 features have most interest — prioritise accordingly | September 2026 | Free | To Do
1.5 | Morning drill content | Upload next 3 months of daily drill content — maintain daily habit | Monthly | Free | To Do
1.6 | Interview guides expansion | Add more questions to existing DA and DS interview guide rounds | Q3 2026 | Free | To Do
Phase 2 — V2.0 Content Creation ¦ Target: Q4 2026 — October to December 2026
Task ID | Task | Description | Target Date | Feature Type | Status
2.1 | Business Analyst track content | Create MCQ questions, flashcards and interview guides for BA role — 3 levels per module | October to November 2026 | Free | To Do
2.2 | ML Engineer track content | Create MCQ questions, flashcards and interview guides for ML Engineer role | November to December 2026 | Free | To Do
2.3 | Data Engineer track content | Create MCQ questions, flashcards and interview guides for Data Engineer role | December 2026 | Free | To Do
2.4 | Company Packs content | Create 50 plus questions for TCS, Infosys, Wipro, Accenture, GIFT City Fintech | October to December 2026 | Pro | To Do
2.5 | Pro subscription flow design | Design complete Pro subscription user journey — upgrade, billing, cancel | November 2026 | Pro | To Do
2.6 | LinkedIn Job Alerts research | Research LinkedIn API integration options — plan technical approach | December 2026 | Pro | To Do
2.7 | AI Chatbot research | Research AI chatbot integration options — define scope and capabilities | December 2026 | Pro | To Do
2.8 | User growth to 500 plus | Continue organic growth — referrals, community, LinkedIn posts | Q4 2026 | Free | To Do
Phase 3 — V2.0 Core Development ¦ Target: Q1 2027 — January to March 2027
Task ID | Task | Description | Target Date | Feature Type | Status
3.1 | Pro subscription — Razorpay | Integrate Razorpay payment gateway — monthly billing at Rs 99 — free trial flow | January 2027 | Pro | To Do
3.2 | Company Packs — build and upload | Build Company Packs section in app — upload all company question content | January to February 2027 | Pro | To Do
3.3 | LinkedIn Job Alerts integration | Build LinkedIn job feed integration — role filter — real-time listings | February 2027 | Pro | To Do
3.4 | Business Analyst track launch | Upload BA content to database — add BA to role selection in app | February 2027 | Free | To Do
3.5 | ML Engineer track launch | Upload ML Engineer content — add to role selection | February to March 2027 | Free | To Do
3.6 | Data Engineer track launch | Upload Data Engineer content — add to role selection | March 2027 | Free | To Do
3.7 | AI Chatbot development | Build in-app AI career assistant — integrate with app | February to April 2027 | Pro | To Do
3.8 | Skill Spider Map | Build visual radar chart showing skill strength across all topics | March 2027 | Free | To Do
3.9 | Admin panel V2.0 updates | Add Company Packs management, Pro user management, revenue dashboard | January to March 2027 | Admin | To Do
Phase 4 — V2.0 Launch and Growth ¦ Target: Q2 2027 — April to June 2027
Task ID | Task | Description | Target Date | Feature Type | Status
4.1 | Pro subscription launch | Go live with Rs 99 per month Pro plan — announce to existing users | April 2027 | Pro | To Do
4.2 | AI Chatbot launch | Launch in-app AI career assistant as Pro feature | April to May 2027 | Pro | To Do
4.3 | National Leaderboard | Build and launch national leaderboard — weekly and monthly rankings | May 2027 | Free | To Do
4.4 | Battle Arena development | Build real-time 1v1 MCQ duel system | April to June 2027 | Pro | To Do
4.5 | Campus Ambassador programme | Launch formal campus ambassador programme for colleges | May 2027 | Free | To Do
4.6 | Mock Interview development | Build structured practice interview with written feedback system | May to June 2027 | Pro | To Do
4.7 | Campus Licensing conversations | Begin enterprise conversations with colleges and placement institutes | Q2 2027 | Enterprise | To Do
4.8 | User growth to 2000 plus | Paid and organic growth — campus ambassadors — LinkedIn — referrals | Q2 2027 | Free | To Do
Phase 5 — V2.0 Scale and V3.0 Planning ¦ Target: Q3 to Q4 2027
Task ID | Task | Description | Target Date | Feature Type | Status
5.1 | Battle Arena launch | Launch 1v1 MCQ duel — requires 2000 plus active users to be useful | July 2027 | Pro | To Do
5.2 | Mock Interview launch | Launch practice interview with feedback as Pro feature | July to August 2027 | Pro | To Do
5.3 | Campus Licensing launch | First enterprise campus licensing deals | Q3 2027 | Enterprise | To Do
5.4 | V3.0 feature scoping | Based on user data and market feedback — define V3.0 feature set | Q4 2027 | Planning | To Do
5.5 | Advanced AI features planning | Plan next generation AI features based on V2.0 AI Chatbot learnings | Q4 2027 | Pro | To Do
5.6 | Regional expansion research | Research expansion to other South Asian markets — Bangladesh, Sri Lanka, Nepal | Q4 2027 | Planning | To Do