## Product Overview
DATA247 — Product Plan v2.0
V2.0 planning document ¦ Post V1.0 launch ¦ Vijetasingh Rajput ¦ 2026
V2.0 Strategic Goals
Field | Details
Primary Goal | Grow active user base to 1000 plus users before any monetisation
Secondary Goal | Launch Pro subscription in Early 2027 after user trust is established
Content Goal | Add Business Analyst, ML Engineer and Data Engineer tracks
Revenue Goal | First revenue in Early 2027 — Rs 5000 to Rs 15000 per month by end of 2027
Community Goal | Grow Telegram community to 500 plus members — t.me/data247prep
Platform Goal | Full Play Store presence with 4.0 plus rating
V2.0 Pro Features — Chargeable at Rs 99 per Month
Field | Details
Company Packs | TCS, Infosys, Wipro, Accenture, GIFT City Fintech — company specific interview questions
LinkedIn Job Alerts | Real-time job listings via LinkedIn integration — filtered by role and location
AI Chatbot | In-app data career assistant — answers preparation and career questions
1v1 Battle Arena | Real-time MCQ duels between two users — competitive preparation
Mock Interview | Structured practice interview with personalised written feedback
Campus Licensing | Enterprise licensing for colleges and placement training institutes
Advanced Analytics | Detailed progress tracking — weak area identification — performance trends
Module Notes Download | Downloadable PDF study notes per topic — view only in V1.0
V2.0 Free Features — Continued from V1.0
Field | Details
MCQ Practice | All existing topics and levels remain free — new role tracks added free
Flashcards | All existing flashcard modules remain free
Morning Drill | Daily drill remains free — builds daily habit
Job Ready Quiz | Diagnostic quiz remains free
Salary Calculator | Salary estimation tool remains free
Learning Roadmap | 12-week plan remains free — dynamic version in Pro
Interview Guides | All existing interview guides remain free
Bookmarks | Save and organise content remains free
Referral System | Referral and rewards system remains free
Streak System | Daily streak tracking remains free
Skill Spider Map | Visual skill radar chart — free feature
National Leaderboard | View leaderboard — free. Detailed stats — Pro
V2.0 New Role Tracks — Free
Field | Details
Business Analyst Track | MCQ practice, Flashcards, Interview Guides — HR, Technical, Behavioural, Managerial rounds
ML Engineer Track | MCQ practice, Flashcards, Interview Guides — model building, deployment, MLOps
Data Engineer Track | MCQ practice, Flashcards, Interview Guides — pipelines, SQL, cloud, orchestration
V2.0 Development Approach
Field | Details
Methodology | Iterative development — launch features one by one — no big bang release
Priority Order | Pro subscription first, then Company Packs, then LinkedIn Job Alerts, then AI Chatbot
Content First | New role track content created before development — same approach as V1.0
User Feedback | Notify Me data from V1.0 drives V2.0 feature priority
Development | Founder-led product — modern development platforms — same approach as V1.0
Timeline | V2.0 development starts Q1 2027 — first features live Q2 2027
V2.0 Success Metrics
Field | Details
User Growth | 1000 plus active users before Pro launch — 3000 plus by end of 2027
Pro Conversion | 2 to 5 percent of active users converting to Pro
Monthly Revenue | Rs 5000 to Rs 15000 per month by end of 2027
Play Store Rating | 4.0 plus rating maintained on Google Play Store
Community | 500 plus members in Telegram community
Retention | 30 percent plus users completing morning drill weekly

## V2.0 Content Plan
DATA247 V2.0 — Content Creation Plan
New content to be created for V2.0 ¦ 2026 to 2027 ¦ Vijetasingh Rajput
NEW ROLE TRACKS — FREE CONTENT
Track | Module | Questions Planned | Flashcards Planned | Interview Guide | Status
Business Analyst | KPIs and Metrics | 60 questions — 3 levels | 30 plus cards | HR, Technical, Behavioural, Managerial | To Do
Business Analyst | Requirement Gathering | 60 questions — 3 levels | 30 plus cards | Included above | To Do
Business Analyst | SQL for BA | 60 questions — 3 levels | 30 plus cards | Included above | To Do
Business Analyst | Excel for BA | 60 questions — 3 levels | 30 plus cards | Included above | To Do
ML Engineer | ML Model Building | 60 questions — 3 levels | 30 plus cards | HR, Technical, Behavioural, Managerial | To Do
ML Engineer | Model Deployment | 60 questions — 3 levels | 30 plus cards | Included above | To Do
ML Engineer | MLOps | 60 questions — 3 levels | 30 plus cards | Included above | To Do
ML Engineer | Python for ML Eng | 60 questions — 3 levels | 30 plus cards | Included above | To Do
Data Engineer | Data Pipelines | 60 questions — 3 levels | 30 plus cards | HR, Technical, Behavioural, Managerial | To Do
Data Engineer | SQL Advanced | 60 questions — 3 levels | 30 plus cards | Included above | To Do
Data Engineer | Cloud and Storage | 60 questions — 3 levels | 30 plus cards | Included above | To Do
Data Engineer | Orchestration Tools | 60 questions — 3 levels | 30 plus cards | Included above | To Do
COMPANY PACKS — PRO CONTENT
Company | Questions Planned | Topics | Format | Pricing | Status
TCS | 50 plus questions | Technical, HR, situational questions specific to TCS hiring pattern | MCQ plus short answer | Pro only — Rs 99 per month | To Do
Infosys | 50 plus questions | Technical, HR, situational questions specific to Infosys hiring pattern | MCQ plus short answer | Pro only — Rs 99 per month | To Do
Wipro | 50 plus questions | Technical, HR, situational questions specific to Wipro hiring pattern | MCQ plus short answer | Pro only — Rs 99 per month | To Do
Accenture | 50 plus questions | Technical, HR, case studies specific to Accenture hiring pattern | MCQ plus short answer | Pro only — Rs 99 per month | To Do
GIFT City Fintech | 50 plus questions | Finance, data, analytics questions for GIFT City roles | MCQ plus short answer | Pro only — Rs 99 per month | To Do