## V1.0 vs V2.0
DATA247 — Version Roadmap v2.0
V2.0 planning document ¦ Prepared post V1.0 launch ¦ Vijetasingh Rajput ¦ 2026
CONTENT FEATURES
# | Feature Area | V1.0 — Launched | V2.0 — Planned (Early 2027) | Pricing in V2.0 | Rationale
1 | MCQ Practice | Data Analyst and Data Scientist — 6 modules each — 3 levels — 60 questions per module | Business Analyst, ML Engineer and Data Engineer tracks added based on user demand | Free — basic tracks. Pro — new role tracks | Launch with two highest demand tracks — expand based on Notify Me data
2 | Flashcards | Data Analyst and Data Scientist — all modules — flip card system | Additional role tracks as new content is created | Free | Demand-led expansion after V1.0 user feedback
3 | Morning Drill | 30 days of drills pre-loaded — manually updated weekly by founder | Automated scheduling system — no manual upload needed | Free | Manual sufficient for launch — automation added at scale
4 | Job Ready Quiz | Data Analyst and Data Scientist — 10 questions each — diagnostic format | Additional role quizzes based on user feedback | Free | Core two roles at launch — expand based on demand
5 | Company Packs | Shown as Coming Soon — Notify Me button active | TCS, Infosys, Wipro, Accenture, GIFT City Fintech question packs | Pro only — Rs 99 per month | Content creation needed — high demand expected based on Notify Me data
6 | Interview Guides | HR, Technical, Behavioural, Managerial — DA and DS — simple English | BA, ML Engineer, Data Engineer interview guides added | Free — existing rounds. Pro — new role guides | Expand based on user demand and feedback
USER TOOLS
# | Feature Area | V1.0 — Launched | V2.0 — Planned (Early 2027) | Pricing in V2.0 | Rationale
7 | Salary Calculator | Education, city, role, experience, skills — salary range output | Quarterly data update — more granular city and role data | Free | Core feature — data refined post-launch with market data
8 | Job Alerts | Basic job alerts section — placeholder for V2.0 integration | Automated LinkedIn job feed integration — real-time listings | Pro only — Rs 99 per month | LinkedIn API integration needed — meaningful only with active job feed
9 | Learning Roadmap | 12-week personalised plan by role and level — static content | Dynamic roadmap — updates based on user progress and weak areas | Free — basic. Pro — personalised dynamic version | Static roadmap at launch — dynamic version needs usage data
10 | Bookmarks | Save questions and flashcards — organised by type | Smart revision reminders based on saved content and performance | Free | Core feature — smart reminders added later
11 | Module Notes | PDF notes upload by admin — free to view in app | Expanded notes library — downloadable for Pro users | Free — view only. Pro — download | Viewing free builds trust — download as Pro incentive
GROWTH AND ENGAGEMENT
# | Feature Area | V1.0 — Launched | V2.0 — Planned (Early 2027) | Pricing in V2.0 | Rationale
12 | Referral System | Unique code per user — reward on successful signup | Tiered referral rewards — leaderboard for top inviters | Free | Core referral live — gamification added at scale
13 | Streak System | Daily drill streak — 7, 30, 100 day milestones | Streak freeze feature — once per month protection | Free | Core streak live — freeze added as users request it
14 | 1v1 Battle Arena | Shown as Coming Soon — Notify Me button active | Real-time MCQ duels between two users | Pro only — Rs 99 per month | Requires active user base of 2000 plus — Month 4 onwards in 2027
15 | National Leaderboard | Shown as Coming Soon — Notify Me button active | Top 100 users nationally — weekly and monthly rankings | Free — view. Pro — detailed stats | Requires 5000 plus active users to be meaningful
16 | AI Chatbot | Shown as Coming Soon — Notify Me button active | In-app data career assistant — answers prep questions | Pro only — Rs 99 per month | Complex integration — planned for Mid 2027 after Pro launch
17 | Mock Interview | Shown as Coming Soon — Notify Me button active | Structured practice interview with personalised feedback | Pro only — Rs 99 per month | Complex feature — planned after AI Chatbot is stable
18 | Skill Spider Map | Shown as Coming Soon — Notify Me button active | Visual radar chart showing strength across all skill areas | Free | Data visualisation feature — needs sufficient user data to be useful
MONETISATION AND PLATFORM
# | Feature Area | V1.0 — Launched | V2.0 — Planned (Early 2027) | Pricing in V2.0 | Rationale
19 | Pro Subscription | Shown as Coming Soon — Notify Me button active | Rs 99 per month via Razorpay — unlocks all Pro features | Pro — Rs 99 per month | Launched after first 500 to 1000 active users — trust built before monetisation
20 | Campus Ambassador | Shown as Coming Soon — Notify Me button active | Formal campus ambassador programme for colleges | Free for ambassadors — drives user growth | Requires stable user base — planned for Mid to Late 2027
21 | Campus Licensing | Not planned for V1.0 | Enterprise licensing for placement cells and colleges | Custom pricing — enterprise | B2B stream — requires V2.0 Pro to be stable first
22 | Play Store | Submission planned after beta validation | Full Play Store presence — ratings, reviews, ASO optimised | Free app — Pro in-app | Post-beta submission — full store presence in V2.0
23 | Admin Panel | Full content management — 8 sections — founder access only | Analytics improvements — user behaviour insights — content performance data | Admin only | Complete at launch — analytics improvements ongoing

## V2.0 Timeline
DATA247 V2.0 — Planned Timeline
Post V1.0 launch planning ¦ Early 2027 target ¦ Vijetasingh Rajput
Quarter | Period | Focus | Key Milestones | Status
Q3 2026 | July to September 2026 | V1.0 Stabilisation | Fix bugs from user feedback. Grow to 200 to 500 users. Collect Notify Me data for V2.0 priorities. Play Store submission. | Planned
Q4 2026 | October to December 2026 | Growth and Preparation | Grow to 500 to 1000 users. Start V2.0 content creation — BA Track, ML Engineer, Data Engineer. Plan Pro subscription flow. | Planned
Q1 2027 | January to March 2027 | V2.0 Development | Build Pro subscription with Razorpay. Build Company Packs. LinkedIn Job Alerts integration. AI Chatbot development starts. | Planned
Q2 2027 | April to June 2027 | V2.0 Launch | Pro subscription goes live. Company Packs live. LinkedIn Job Alerts live. New role tracks go live. Battle Arena development. | Planned
Q3 2027 | July to September 2027 | V2.0 Growth | Campus Ambassador programme launch. Battle Arena beta. National Leaderboard launch. Mock Interview development. | Planned
Q4 2027 | October to December 2027 | V3.0 Planning | Campus Licensing enterprise conversations. Advanced AI features planning. V3.0 feature scoping based on user data. | Planned